## Sheet1
Input | Schelduled Progess
Actual Progess
Budget
Cost
Formula
Step1: Collecting task information
Planned Value | PV | Schelduled Progess*Budget
Actual cost | AC | current costs
Earned value | EV | Actual Progess*budget
Step2: Evaluating performance
Cost Performance Index | CPI | EV / AC | or | Cost Variances | (EV-AC)/EV
| CPI > 1 | Under Budget
| CPI < 1 | Over Budget
| CPI = 1 | Exactly on budget
Schedule Performance Index | SPI | EV / PV |  | Schedule Variance | (EV-PV)/PV
| SPI > 1 | Ahead of schedule
| SPI < 1 | behind schedule
| SPI = 1 | Exactly on schedule
Step3 Making Prediction
Estimate to complete | ETC | (Total budget - EV) / CPI
ETC | Remaining cost completing the project
Estimate at compleion | EAC | AC + ETC
EAC | Total cost of completing the project